## Schedule
STATUS OF VARIOUS PROCEDURE BEING PREPARED AT NLDC UNDER IEGC 2023
Sl. No. | Procedure | IEGC regulation | Date of uploading draft Procedure on NLDC/RLDC website | Stakeholder workshop date/time | Last date for submission of comments by stakeholders | Stakeholder consultation | Submission by NLDC | CERC Approved/Noted | Remarks
Operating Procedure (for information of Hon'ble CERC)
1 | NLDC Operating Procedure(consolidated) | Operating Code: Regulation No. 28(3) | 22.09.2023 | 26.09.2023 (10:30-13:00) | 27.09.2023 | Completed | 29.09.2023
2 | Formats for testing plan and periodic tests reports | Operating Code: Regulation No. 40 (2) | 18.08.2023 | 24.08.2023 (10:30 - 1330 hrs) | 30.08.2023 | Completed | 25.09.2023
3 | Dynamic reactive power reserve assessment | Operating Code: Regulation No. 39 (6), 35(1) | 23.08.2023 | 01.09.2023 (10:30hrs) | 05.09.2023 | Completed | 15.09.2023 | Noted by CERC for information on 28.09.2023
4 | Performance evaluation of SRAS, TRAS providers | Operating Code: Regulation No. 30(13) | 01.09.2023 | 07.09.2023 | 15.09.2023 | Completed | 20.09.2023 | Noted by CERC for information on 28.09.2023
5 | Resource Adequacy Accessment and Operational Planning | Resource Planning Code: Regulation No. 5(3)€ | 11.09.2023 | 18.09.2023 | 20.09.2023 | Completed | 25.09.2023
6 | Detailed Procedure covering modalities for carrying out interconnection studies | (Connection Code: Regulation No. 10(3)) | 14.07.2023 | 01.08.2023 (10:30hrs) | 07.08.2023 | Completed | 25.08.2023 | Noted by CERC for information on 28.09.2023
Procedures for (for information of Hon'ble CERC)
7 | Grant of Temporary General Network Access (T-GNA) to the inter-State Transmission system through National Open Access Registry (NOAR) | Connectivity and GNA Regulation 2022 | 06.10.2022 | 13.10.2022, 21.10.2022 and 27.10.2022 | 07.11.2022 | Completed | 14.07.2023 | Noted by CERC for information on 29.09.2023
8 | Cyber Security Framework | Cyber Security: Regulation No. 50(3) | 18.08.2023 | 25.08.2023 (10:30-13:30) | 31.08.2023 | Completed | 15.09.2023 | Noted by CERC for information on 28.09.2023
Procedures for (for Approval of Hon'ble CERC)
9 | First time energization and integration of new or modified power system elements | Connection Code: Regulation No. 8(2) | 25.08.2023 | 05.09.2023 (10:30 - 1330 hrs) | 22.09.2023 | Completed | 28.09.2023
10 | Hot, Warm, cold start; SCUC, Unit Shut down, SCED, sharing of net gains | Scheduling & Despatch Code: Regulation No. 46 (4)(i), 46 (4)(j), 46 (5)(a), 46 (5(b), 49 (2)(a)(iv), 49 (2)(a)(xi) | 07.09.2023 | 14.09.2023 | 25.09.2023 | Completed | 29.09.2023 | Approved on 16.04.2024
11 | Procedure for aggregation of pooling stations for the purpose of combined scheduling and deviation settlement for wind or solar or renewable hybrid generating stations | Scheduling and Despatch Code: Regulation No. 45 (11)(b)) | 11.09.2023 | 19.09.2023 | 25.09.2023 | Completed | 03.07.2024
12 | Detailed Procedure for Assessment of quantum of Secondary & Tertiary Reserve Capacity, along with Information Exchange and Timelines | Operating Code: Regulation No. 30(11)(k), 30(11)(q), 30(12)(d), 30(12)(1) | 07.08.2023 | 26.07.2022-27.07.2022 | 22.08.2023 | Completed | 20.09.2023 | Final CERC order published on 28.09.2023
13 | Detailed Procedure for allocation of Transmission Corridor for Scheduling of GNA and T-GNA Transactions and Transfer capability assessment methodology. | (CERC GNA Regulation 2022) | 10.11.2022 | 01.12.2022 | 18.12.2022 | Completed | 14.07.2023 | Final CERC order published on 29.09.2023
14 | Procedure for sharing of net savings in day ahead market,real time collective market for generating stations whose tariff is determined under section 62 of Act. | Scheduling and Despatch Code: Regulation No. 48 (3)(e)) | 29.09.2023 | 30.10.2023 | 06.11.2023 | To be scheduled | - | - | NLDC vide Letter to CERC dated 22.7.24 communicated about no longer need of procedure due to effectiveness of Taraiff Regulations 2024.
15 | Compensation for synchronous condenser mode operation | (Operating Code: Regulation No. 39 (10))
16 | Compensation of quick start synchronous generation | (Operating Code: Regulation No. 30(9))
17 | Methodology for allocation of cost of procurement of Secondary/Tertiary reserve capacity in case of shortfall of reserve capacity by the State (Portal for States to upload reserves maintained intra-state) | (Operating Code: Regulation No. 30(11)(t),30(12)(h))
18 | Procedure for payment for Black start support | (Operating Code: Regulation No. 34 (9)) | 23.10.2023 | 30.10.2023 | 06.11.2023 |  | 25.07.2024
19 | Supply from alternate REGS source: sharing of net savings for generating stations whose tariff is determined under Section 62 of the Act. | (Scheduling and Despatch Code: Regulation No. 48(3)(e )) | 23.10.2023 | 30.10.2023 | 06.11.2023 |  | - | - | NLDC vide Letter to CERC dated 22.7.24 communicated about no longer need of procedure due to effectiveness of Taraiff Regulations 2024.

## Grid India Plan (hidden)
Procedures to be prepared by NLDC and RLDCs in IEGC, 2023
S.No | Name of Procedure/Drafting Responsibilities |  | Remarks | Lead LDC (NLDC/RLDC) | Exceutive(s) from NLDC
1 | Procedures related to Ancillary Services |  |  | NLDC | Sh. KVN Pawan Kumar/ Sh. Phanisankar Chilukuri
| 1(a). Assessment of quantum of secondary reserve capacity (Operating Code: Regulation No. 30(11)(k)) | For Approval | Submitted for approval
| 1(b). Information exchange and timelines in respect of Secondary/Tertiary reserves (Operating Code: Regulation No. 30(11)(q), 30(12)(d),30(12)(l)) | For Information | Submitted for approval
2 | Detailed procedure covering modalities for first time energization and integration of new or modified power system elements (Connection Code: Regulation No. 8(2)) | For Approval | Draft ready, under consultation with RLDC |  | Sh. Abhijeet Prakash/ Sh. Priyam Jain
3 | Detailed Procedure covering modalities for carrying out interconnection studies (Connection Code: Regulation No. 10(3)) | For Information | Draft submitted, Stakeholder workshop conducted on 01st Aug |  | Sh. Priyam Jain/ Sh. Gaurab Dash
4 | Detailed Procedure for allocation of Transmission Corridor for Scheduling of GNA and T-GNA Transactions (CERC GNA Regulation 2022) | For Approval | Submitted for approval |  | Sh. Priyam Jain/ Sh. Prabhankar Porwal
S.No | Name of Procedure/Drafting Responsibilities |  | Remarks | Lead LDC (NLDC/RLDC) | Exceutive(s) from NLDC | Exceutive(s) from Lead RLDC
5 | Operating Procedure of NLDC and RLDC (Operating Code: Regulation No. 28(3) and 28(4)) |  | Stakeholder consultation required | NLDC | Sh. Manas Ranjan Chand / Sh. Rohit Anand
| 5(a). Formats for data exchange for demand estimation (Operating Code: Regulation No. 31 (2)) | To be submitted for information after stakeholder consultation | Completed | NERLDC | Sh. Vaibhav Chandra Dass/ Sh. Anuj Kumar | Ms. Sangita Das Sh. Chitra B. Thapa
| 5(b). Resource adequacy and operational planning (Operating Code: Regulation No. 31 (1)(c )) |  | Brainstorming | NRLDC | Sh. Aman Gautam/ Sh. Rahul Kumar Jorwal | Sh. Gaurav Malviya Sh. Saravana Prakash
| 5(c ). List of Important Grid elements (Operating Code: Regulation No. 29 (2)(b)) |  | Completed | NERLDC | Sh. Mohit Kumar Gupta/ Sh. Aman Gautam | Sh. Sachin Kumar Singh Sh. Manjit Choudhury.
| 5(d). Procedure for Outage coordination (Operating Code: Regulation No. 32 (3)) |  | Draft prepared and forwarded to RPC/NPC for stakeholder consultation | WRLDC | Sh. Pradeep Meena/ Sh. Amit Pushkar | Shri. Manoj Thakur Shri. Venkateswara Rao Shri. Omkar Kumbar
| 5(e ). Procedure and formats for real-time monitoring/ assessment (Operating Code: Regulation No. 31 (1)(c )) |  | Brainstorming | WRLDC | Sh. Anuj Kumar/ Sh. Rahul Jorwal | Shri. G. Madhukar Shri. Akhil Gupta
| 5(f). Format for data submissions and updating (Operating Code: Regulation No. 31 (1)(c )) |  | Brainstorming | WRLDC | Sh. Anuj Kumar | Shri.Tushar Mohapatra Shri. Shaikh Mastanvali
| 5(g). FRC and FRO computation methodology (Operating Code: Regulation No. 30 (10)(f )) |  | Draft ready for public consultation | NRLDC | Sh. Abhishek Gautam | Sh. Deepak Kumar Ms. Sugata Bhatacharya
| 5(h). Transfer capability assessment methodology (Operating Code: Regulation No. 33 (5)) |  | Draft ready for public consultation | ERLDC | Sh. Prabhankar Porwal/ Sh. Gaurab Dash | Saibal Ghosh Pritam Mukherjee
| 5(i). Dynamic reactive power reserve assessment (Operating Code: Regulation No. 39 (6)) |  | Draft ready for stakeholder consultation in next | SRLDC | Sh. Aman Gautam | Venkateshan.M MVL Rajendra
| 5(j). Criteria to categorise system state ((Operating Code: Regulation No. 35(1)) |  |  | SRLDC | Sh. Rahul Shukla | Venkateshan.M Sanyasi Naidu
| 5(k). Formats for testing plan and periodic tests reports (Operating Code: Regulation No. 40 (2)) |  | Draft is being deliberated with RLDCs | SRLDC | Sh. Rahul Shukla | T. Muthukumar A Janardhan
| 5(l). Formats for reporting forecast errors (Operating Code: Regulation No. 37 (1)(a)) |  | Completed | NRLDC | Sh. Abhijeet Prakash/ Ms. Priyanka Meena | Sh. Paritosh Pathak Sh. Lav khandelwal
| 5(m). Post despatch reporting formats (Operating Code: Regulation No. 37(1) and 37 (2)) |  | Completed | ERLDC | Sh. Abhishek Gautam | Sourav Mondal Akash Modi
| 5(n). Format for declaration of grid disturbance (Operating Code: Regulation No. 37 (2)) |  | Draft is being deliberated with RLDCs | NERLDC | Sh. Manas Ranjan Chand/ Sh. Aman Gautam | Sh. Subhash Kumar Sh. Utpal Das
| 5(o). Cyber Security Framework (Cyber Security: Regulation No. 50(2)) |  | Draft under development | WRLDC | Sh. A B Sengupta | Shri.Sunil Patil Sanjeet Choudhary
6 | Procedure for aggregation of pooling stations for the purpose of combined scheduling and deviation settlement for wind or solar or renewable hybrid generating stations (Scheduling and Despatch Code: Regulation No. 45 (11)(b)) | For Approval | Draft is being deliberated with RLDCs | NRLDC | Sh. Debajyoti Majumder | Sh. Pankaj Kumar Sh. Ajit Kumar Yadav
7 | Procedures related to SCUC and SCED |  |  | NLDC and SRLDC
| 7(a). Detailed procedure to start a unit under different conditions such as HOT, WARM and COLD (Scheduling and Despatch Code: Regulation No. 46 (4)(i)) | For Approval | Brainstorming |  | Sh. Saif Rehman Sh Phanisankar | T MuthuKumar Ajith Ganji
| 7(b). Procedure for unit shutdown and arranging supply from other station |  |  |  |  | Nadim Ahmad DVS Phaneendra
| 7(c ). Detailed procedure for participation of the generating stations other than those whose tariffs are determined under Section 62 of the Act opting to participate in SCUC (Scheduling and Despatch Code: Regulation No. 46 (4)(j)) |  |  |  |  | T MuthuKumar Sreehari
| 7(d). Assessment of adequacy or inadequacy of reserves and identification of the generating stations/units for SCUC (Scheduling and Despatch Code: Regulation No. 46 (5)(a), 46 (5)(b)) |  |  |  |  | T MuthuKumar Vamshi Ballikonda
| 7(e ). Detailed procedure for SCED (Scheduling and Despatch Code: 49(2)(a)(iv)) | For Information |  |  |  | T MuthuKumar Abhishek
| 7(f). Detailed procedure for SCED: sharing of net savings (Scheduling and Despatch Code: 49(2)(a)(xi)) | For Approval |  |  |  | Nadim Ahmad Praharsha
8 | Detailed Procedure for evaluating control area wise performance of SRAS, TRAS providers (Operating Code: Regulation No. 30(13)) | For Information |  | NLDC | Sh. Anmol Sharma | -
9 | Template for System restoration Procedures of RLDC and SLDC (Operating Code: Regulation No. 34 (1), 34(2)) | For Information | Draft under development | ERLDC | Sh. Abhishek Gautam/ Sh. Mohit Kumar Gupta | Chandan Kumar Alok Pratp Singh
S.No | Name of Procedure/Drafting Responsibilities |  | Target Date | Lead LDC (NLDC/RLDC) | Exceutive(s) from NLDC
10 | Sharing of net savings from sale in day ahead collective market, for generating stations whose tariff is determined under Section 62 of the Act. (Scheduling and Despatch Code: Regulation No. 49(1)(l)) | For Approval | Draft under preparation | NLDC | Sh. Anupam Kumar
11 | Compensation for synchronous condenser mode operation (Operating Code: Regulation No. 39 (10)) | For Approval |  |  | Sh. Subhendu Mukherjee
12 | Compensation of quick start synchronous generation (Operating Code: Regulation No. 30(9)) | For Approval |  |  | Sh. Subhendu Mukherjee
13 | Methodology for allocation of cost of procurement of Secondary/Tertiary reserve capacity in case of shortfall of reserve capacity by the State (Portal for States to upload reserves maintained intra-state) (Operating Code: Regulation No. 30(11)(t),30(12)(h)) | For Approval |  |  | Sh. Subhendu Mukherjee
14 | Procedure for payment for Black start support (Operating Code: Regulation No. 34 (9)) | For Approval |  |  | Sh. Anupam Kumar
15 | Supply from alternate REGS source: sharing of net savings for generating stations whose tariff is determined under Section 62 of the Act. (Scheduling and Despatch Code: Regulation No. 48(3)(e )) | For Approval |  |  | Sh. Anupam Kumar
Responsibilities of Executives from NLDC/RLDCs: (i) Executive(s) from Lead LDC would be responsible for drafting and finalizing the procedure with inputs from all RLDCs, NLDC and other stakeholderswithin the target date. (ii) Executive(s) from Lead LDC would coordinate for submission of procedure to CERC for approval/information. The suggestions/advise received from CERC shall be incorporated. Note: (i) 02 nos. executives may be deputed from Lead RLDC for the assigned responsibilities. (ii) Sh. Manas Ranjan Chand (DGM) and Sh. Rohit Anand (CM) would be overall coordinator responsible for finalization of Operating Procedure of NLDC and RLDC. Respective formats/procedures constituting part of the Operating Procedure shall be prepared as per assigned responsibilities.